## Timeline
| September |  |  | October |  |  | November |  |  | December
Jared | Learning Git |  | Learning Gantt |  | Login Screen |  | Save/Load | Save/Load | Encryption Small fixes | Small fixes, bug fixes, testing
AJ |  | Learning Git Learning Atom | Learning Gantt |  |  | Backend | Save/Load MVC | MVC Testing | Printing functionality
Kyle |  | Learning Git Learning Atom | Learning Gantt |  |  | Initial Screen | Table Filters | Transactions Testing | Labels Integration Testing Bug fixes
Keysha | [5 empty] | Testing | User Guide Benefits Calculator | Logo Codes User Guide | Codes Documentation

## Notes
TIME
| AJ | Kyle | Jared | Keysha
Learning Git | Sept 11th - 6:30 to 9:00 | Sept 11th - 12:00 to 12:30 | Sept 7th - 9:30 to 12:30
| 2.5 | 1.5 | 3
Learning Atom | Sept 13th - 7:00 to 10:00 | Sept 13th - 2:40 to 5:40 | Sept 12th - 9:30 to 11:00
| 3 | 3 | 2.5
Learning Gantt | Sept 26th - 7:00 to 9:00 | Sept 26th - 7:00 - 8:30 | Sept 26th - 5:30 to 7:00
| 2 | 1.5 | 1.5
Atom Package | Oct 4th - 6:00 to 6:30
0.5
Sprint 1 | Oct 16th - 6 to 7 Oct 18th - 7 to 12 | Oct 11th – 3:00 to 8:00;14th 12 to 4 | Oct 16th - 9:30 to 11:50; 17th - 10 to 11 | Oct 18th - 12:30 PM- 2:00 PM
| 6 | 7 | 3.25 | 1.5
Sprint 1 Notes | Powerpoint, UML, Backend, and Code integegration | Initial Screen | Login Screen | Configuration Integration and Testing
Sprint 2 |  | Oct. 21 12-3; 22 12-2 | Oct 29th - 2:30 - 3:00, 9:55 - 10:30; 31st - 1:00 - 4:05 | Oct 30th - 8 PM - 9 PM; Nov 2nd - 11:30PM - 2 AM, 11 AM - 12 PM
| 5.5 |  | 4 | 4.5
Sprint 2 Notes | Integrating code, save/load transactions, pulling model through controller from view classes | table filters,transaction functionality | Small improvements to Login Screen, Save/Load | User guide, Benefits calculator, Input validation
Sprint 3 |  | Nov. 11 12-4; Nov. 12 12-4 | Nov. 8th 4-5:30 9th 9 - 10:30, 10th 10-11, 13th 6-8 | Nov 12th - 7 PM - 10 PM; Nov 13th 11 PM - 12 AM
| 3 | 8 | 6 | 5
Sprint 3 Notes | Implementation of singleton, mvc work, testing. | Integration, testing, more transaction functionality | Save and Load functionality, Testing | Updated user guide & input sanitization, added logo, started implementing code functionality
|  | Nov. 17 12-4; Nov. 18 6-10 | Nov. 16th 9:45 - 10:45, 19th 6-10 | Nov 26th - 4 PM - 6 PM; Nov 27th 2 PM - 3 PM; 6 PM - 8 PM
Sprint 4 | 3 | 8 | 5 | 5
Sprint 4 Notes | Added printing functionality, made presentation | Tested code, added more balance labels, integration, build process | Finished changes made check, encryption | Functionality for new expense/deposit codes, software documentation
Sprint 5 | 3.5 | 6 | 3 | 4
|  | Nov. 30 12-3; Dec. 1 12-3 | Nov. 30th 9:45 - 10:45 Dec. 4th 5-7 | Dec 3rd - 5 PM - 6 PM; Dec 4th - 6 PM - 7 PM; 9 PM - 11 PM
Sprint 5 Notes | Worked with backgrounds, added menu bar color, did MVC UML, made presentation, started on timeline conversion | tested code, modified creation of accounts, integrated code | Minor convenience updates, added transaction code descriptions | Added save/load functionality for transaction codes, worked on software documentation.